## wanna create a gantt chart with
Task | Duration (Days) | Start Date | Finish Date | Predecessor (Task Must Finish First)
Project Setup & Core
Forms finalization (applications) | 2 | 2025-10-13 | 2025-10-14 | -
ER Drawing | 1 | 2025-10-15 | 2025-10-15 | Forms finalization
Database creation | 3 | 2025-10-16 | 2025-10-20 | ER Drawing
Backend - Seeker
Seeker: Login, registration (with SMTP) | 2 | 2025-10-21 | 2025-10-22 | Database creation
Seeker: Home page (available jobs show) | 5 | 2025-10-23 | 2025-10-29 | Seeker: Login, registration
Seeker: Documents | 3 | 2025-10-30 | 2025-11-03 | Seeker: Home page
Seeker: Profile | 3 | 2025-11-04 | 2025-11-06 | Seeker: Documents
Seeker: Application | 5 | 2025-11-07 | 2025-11-13 | Seeker: Profile
Backend - Admin
Admin: Login | 2 | 2025-11-13 | 2025-11-17 | Database creation
Admin: Seekers list | 3 | 2025-11-17 | 2025-11-19 | Admin: Login
Admin: Client list | 4 | 2025-11-20 | 2025-11-24 | Admin: Seekers list
Admin: Posted jobs | 4 | 2025-11-24 | 2025-11-28 | Admin: Client list
Admin: Invoice | 4 | 2025-12-01 | 2025-12-05 | Admin: Posted jobs
Admin: Scheduled | 4 | 2025-12-05 | 2025-12-10 | Admin: Invoice
Admin: Home | 3 | 2025-12-10 | 2025-12-15 | Admin: Scheduled
Backend - Client
Client: Home (Current Jobs Posted) | 5 | 2025-12-15 | 2025-12-22 | Database creation
Client: Post New Job | 3 | 2025-12-22 | 2025-12-25 | Client: Home
Client: MSL Alerts | 8 | 2025-12-25 | 2026-01-02 | Client: Post New Job
Client: Invoice and current agreement | 4 | 2026-01-02 | 2026-01-06 | Client: MSL Alerts
Final Stages
Check all functions | 3 | 2026-01-06 | 2026-01-09 | Client: Invoice, Seeker: Application, Admin: Home
Testing | 5 | 2026-01-09 | 2026-01-16 | Check all functions
Hosting | 5 | 2026-01-19 | 2026-01-23 | Testing
Launch | 1 | 2026-01-26 | 2026-01-26 | Hosting